## Summary
TOURZINA — BUG REPORT SUMMARY
Platform: Tourzina (dev.tourzina.com) ¦ Tester: Ahmed Salah ¦ Date: Apr–May 2026
Total Bugs | Open
Critical | In Review
High | Resolved
Medium | Rejected
Low | Resolution Rate

## Bug Log
Bug ID | Module | Title | Type | Severity | Platform | Status | Date Reported | Steps to Reproduce | Expected Result | Actual Result | Notes
BUG-001 | Cart | Users cannot reduce or edit ticket quantity in cart | FUNCTIONAL | HIGH | Website | In Review | 29-Apr-2026 | 1. Add multiple tickets to cart 2. Navigate to cart 3. Attempt to reduce quantity | User can increase or decrease ticket quantity inside the cart | No option to reduce quantity. Must remove entire item and re-add | Blocks user from adjusting order — major UX issue
BUG-002 | Cart | No confirmation message when ticket is added to cart | UI | MEDIUM | Website | In Review | 29-Apr-2026 | 1. Browse an activity 2. Click 'Add to Cart' | Confirmation toast/message: 'Item added to cart' | No feedback shown. User unsure if item was added | Causes repeated clicks and cart duplicates
BUG-003 | Cart | Add to Cart button stuck in loading state | UI | HIGH | Website | Resolved | 29-Apr-2026 | 1. Click 'Add to Cart' on any ticket 2. Observe button state | Button shows loading briefly then confirms success | Button stays in loading state indefinitely. No cart update occurs
BUG-004 | Booking | Multiple users can book the same in-progress ticket | UI | CRITICAL | Website | Open | 29-Apr-2026 | 1. User A starts booking ticket 2. Status changes to In Progress 3. User B books same ticket simultaneously | Ticket is locked/reserved during booking — only one user can proceed | Both users can book the same ticket at the same time | Can cause overselling and booking conflicts
BUG-005 | Admin Dashboard | Payout Requests tab shows inaccurate/outdated data | UI | CRITICAL | Admin Dashboard | Open | 29-Apr-2026 | 1. Login as Admin 2. Navigate to Payout Requests tab 3. Check amounts, statuses, timestamps | Accurate, real-time payout request data displayed | Incorrect amounts, wrong statuses, missing new requests | Prevents admins from approving payouts reliably
BUG-006 | Partner Dashboard | Content Creator Support has access to admin/user tickets | UI | CRITICAL | Partner Dashboard | Open | 29-Apr-2026 | 1. Login as Content Creator 2. Navigate to Support feature 3. View available tickets | Content Creator sees only their own support tickets | Full access to admin and all user tickets is exposed | RBAC violation — sensitive data exposure
BUG-007 | Partner Dashboard | Settings tab does not save data changes for Content Creator | FUNCTIONAL | HIGH | Partner Dashboard | Open | 29-Apr-2026 | 1. Login as Content Creator 2. Go to Settings tab 3. Edit profile fields 4. Save | Changes are saved and reflected immediately | Fields locked or changes not saved | Prevents creators from managing their account
BUG-008 | Partner Dashboard | Archive feature not working for content creator links | FUNCTIONAL | MEDIUM | Partner Dashboard | Rejected | 29-Apr-2026 | 1. Login as Content Creator 2. Go to Links section 3. Click Archive on a link | Link is archived and moved to archived state | No action occurs. Link remains active
BUG-009 | Partner Dashboard | Overview tab displays incorrect Estimated Balance | UI | HIGH | Partner Dashboard | In Review | 29-Apr-2026 | 1. Login as Content Creator 2. Navigate to Overview tab 3. Check Estimated Balance | Estimated Balance matches actual records | Inaccurate balance shown — misaligned with real data | Undermines dashboard reliability
BUG-010 | Partner Dashboard | Create New Link feature not working | FUNCTIONAL | HIGH | Partner Dashboard | Resolved | 29-Apr-2026 | 1. Login as Content Creator 2. Click 'Create New Link' | New link is created and saved | No response. No link generated
BUG-011 | Voucher | Voucher not sent to email after generation | UI | HIGH | Website | In Review | 29-Apr-2026 | 1. Complete a booking 2. Generate voucher 3. Check registered email inbox | Voucher PDF sent to user's registered email | No email received. Voucher only visible on website | User cannot access voucher without logging in
BUG-012 | Admin Dashboard | Duplicate X icons in booking details | UI | LOW | Admin Dashboard | Resolved | 29-Apr-2026 | 1. Login as Admin 2. Open any booking details | Single X (close) icon displayed | Two X icons displayed simultaneously | Minor UI clutter
BUG-013 | Voucher | Voucher download feature not working | UI | CRITICAL | Website | Resolved | 29-Apr-2026 | 1. Complete booking 2. Click 'Download Voucher' | Voucher PDF downloaded to device | No response. File not generated or saved | User cannot retrieve voucher
BUG-014 | Voucher | Ticket voucher does not include QR code | UI | CRITICAL | Website | Open | 28-Apr-2026 | 1. Complete booking 2. Download ticket voucher 3. Inspect voucher for QR code | QR code present on voucher for scanning at event | No QR code included in voucher | Staff cannot verify tickets at check-in
BUG-015 | Staff Dashboard | Staff can edit partners (should be view-only) | FUNCTIONAL | HIGH | Staff Dashboard | In Review | 28-Apr-2026 | 1. Login as Staff 2. Go to Partner tab 3. Attempt to edit partner details | Partner tab is view-only for staff | Staff can edit partner records | RBAC violation
BUG-016 | Booking | User can order more tickets than admin availability limit | UI | CRITICAL | Website | In Review | 28-Apr-2026 | 1. Admin sets ticket availability to 2 2. User attempts to order 3+ tickets | System enforces the 2-ticket limit | User can order beyond the set limit | Causes overselling and inventory inaccuracy
BUG-017 | Website | Destinations tab shows only 6 destinations | UI | MEDIUM | Website | In Review | 28-Apr-2026 | 1. Navigate to Destinations tab | All available destinations displayed | Only 6 destinations shown — full list only visible via 'View All' | Inconsistent display
BUG-018 | Search/Filter | Price filter range capped at $0–$500 | FUNCTIONAL | HIGH | Website | In Review | 28-Apr-2026 | 1. Go to booking page 2. Apply price filter | Filter range reflects actual ticket prices including those above $500 | Range always shows $0–$500. Tickets priced above $500 (e.g. $900) not filterable
BUG-019 | Admin Dashboard | Admin cannot edit missions in Rewards & Vouchers Console | FUNCTIONAL | HIGH | Admin Dashboard | In Review | 28-Apr-2026 | 1. Login as Admin 2. Go to Rewards & Vouchers Console 3. Try to edit Welcome Bonus mission | Admin has full edit access to all missions | Edit option missing, disabled or permission blocked
BUG-020 | Admin Dashboard | Admin cannot create missions in Rewards & Vouchers Console | FUNCTIONAL | HIGH | Admin Dashboard | Rejected | 28-Apr-2026 | 1. Login as Admin 2. Go to Rewards & Vouchers Console 3. Try to create new mission | Admin can create new missions | Option missing or blocked
BUG-021 | Staff Dashboard | No data displayed in Inventory tab for staff | UI | HIGH | Staff Dashboard | Rejected | 28-Apr-2026 | 1. Login as Staff 2. Navigate to Inventory tab | Inventory records displayed | Section is empty despite records existing in system
BUG-022 | Staff Dashboard | No data displayed in Activities tab for staff | FUNCTIONAL | HIGH | Staff Dashboard | Rejected | 28-Apr-2026 | 1. Login as Staff 2. Navigate to Activities tab | Activities listed and visible | Section empty despite activities existing
BUG-023 | Staff Dashboard | Booking tab does not display bookings | UI | HIGH | Staff Dashboard | Rejected | 28-Apr-2026 | 1. Login as Staff 2. Navigate to Booking tab | All bookings listed | Section blank or fails to load
BUG-024 | Staff Dashboard | Analytics dashboard shows inaccurate numbers for staff | FUNCTIONAL | HIGH | Staff Dashboard | In Review | 28-Apr-2026 | 1. Login as Staff 2. View Analytics dashboard 3. Compare with actual transaction logs | Accurate analytics matching actual data | Reported numbers do not match actual database values
BUG-025 | Website | Reviews carousel scrolls too fast — unreadable | UI | HIGH | Website | In Review | 28-Apr-2026 | 1. Navigate to homepage reviews section 2. Observe 'Real experiences from real travelers' carousel | Auto-scroll at readable pace or user-controlled | Carousel moves too fast. Reviews disappear before user can read them
BUG-026 | Website | Page resets to top after language change | UI | MEDIUM | Website | In Review | 28-Apr-2026 | 1. Scroll halfway down an activity page 2. Change website language | Page reloads in new language preserving scroll position | Page reloads and resets to top, losing user's position
BUG-027 | Website | English punctuation misaligned in Arabic interface | UI | MEDIUM | Website | In Review | 28-Apr-2026 | 1. Set website language to Arabic 2. View any English text content | English full stop appears at end of sentence | Period appears at beginning of sentence | RTL/LTR rendering issue
BUG-028 | Cart | User must proceed with all cart items — no single item checkout | UI | HIGH | Website | In Review | 28-Apr-2026 | 1. Add multiple tickets to cart 2. Attempt to checkout only one item | Option to select individual items for checkout | All items forced into checkout together | Limits user flexibility
BUG-029 | Voucher | Voucher PDF only available during booking — not after confirmation | UI | HIGH | Website | In Review | 28-Apr-2026 | 1. Complete booking 2. Navigate away from confirmation page 3. Try to re-download voucher from booking history | Voucher downloadable any time from account/booking history | Download only available during booking flow. Not accessible after
BUG-030 | Booking | User unable to request ticket cancellation | UI | HIGH | Website | In Review | 28-Apr-2026 | 1. Login 2. Go to booking history 3. Try to cancel a booking | Cancellation option available for booked tickets | Button missing, disabled, or non-functional
BUG-031 | Search | Search does not provide proper suggestions | FUNCTIONAL | MEDIUM | Website | In Review | 28-Apr-2026 | 1. Click search bar 2. Type a query | Relevant suggestions appear | Suggestions unrelated or missing entirely
BUG-032 | Search | Search suggestions only appear after 3 characters | FUNCTIONAL | MEDIUM | Website | In Review | 28-Apr-2026 | 1. Click search bar 2. Type 1–2 characters | Suggestions appear from first character | No suggestions until 3 characters entered
BUG-033 | Cart | Cart item count unclear when exceeding 100 tickets | UI | MEDIUM | Website | In Review | 28-Apr-2026 | 1. Add more than 100 tickets to cart 2. Check cart counter | Counter displays exact number clearly | Digits overlap, truncate, or become visually unclear
BUG-034 | Search/Filter | Date filter returns all bookings instead of filtered results | FUNCTIONAL | HIGH | Website | Rejected | 28-Apr-2026 | 1. Go to booking page 2. Apply date filter 3. Observe results | Only bookings within selected date range shown | All bookings displayed regardless of filter | Filter completely non-functional
BUG-035 | Reviews | User unable to post a review on activity | FUNCTIONAL | MEDIUM | Website | In Review | 28-Apr-2026 | 1. Open an activity page 2. Fill in review form 3. Click Submit | Review posted and visible on activity page | Submit fails silently. No confirmation. Review not posted
BUG-036 | Email | Confirmation email not received after ticket booking | FUNCTIONAL | HIGH | Website | Rejected | 28-Apr-2026 | 1. Complete ticket booking 2. Check inbox of registered email | Confirmation email delivered immediately after booking | No confirmation email received
BUG-037 | Security | User session does not expire after inactivity | SECURITY | HIGH | Website | Open | 28-Apr-2026 | 1. Login to website 2. Leave tab open without activity for extended period | Session expires and user is automatically logged out | User remains logged in indefinitely | Security risk on shared/public devices
BUG-038 | UI | Welcome text cut off in landscape orientation on mobile | UI | HIGH | Website | In Review | 28-Apr-2026 | 1. Open website on mobile in portrait 2. Rotate to landscape | Welcome text adjusts to fit landscape layout | Text cut off — only half visible in landscape mode
BUG-039 | Supplier Dashboard | Multiple partner applications accepted but only last reflects | FUNCTIONAL | HIGH | Supplier Dashboard | Open | 28-Apr-2026 | 1. Submit multiple role applications (supplier, affiliate, content creator) 2. Approve all | All approved roles reflected in system | Only last approved application reflected
BUG-040 | Admin Dashboard | Partner application can be approved after rejection | FUNCTIONAL | HIGH | Admin Dashboard | Open | 28-Apr-2026 | 1. Reject a partner application 2. Attempt to approve same application later | Rejected application cannot be re-approved | Record persists and can be approved after rejection | Workflow logic flaw
BUG-041 | Security | Affiliate can request payout (should be read-only) | SECURITY | HIGH | Supplier Dashboard | In Review | 28-Apr-2026 | 1. Login as Affiliate 2. Navigate to Finance tab 3. Attempt payout request | Affiliate Finance tab is read-only | Affiliate can submit payout requests | RBAC violation
BUG-042 | Security | Affiliate can cancel/confirm bookings (should be read-only) | FUNCTIONAL | HIGH | Admin Dashboard | In Review | 28-Apr-2026 | 1. Login as Affiliate 2. Navigate to bookings 3. Attempt to cancel or confirm | Affiliates have view-only access to bookings | Affiliates can cancel and confirm bookings | RBAC violation
BUG-043 | Security | Supplier account active after ban/freeze | SECURITY | CRITICAL | Admin Dashboard | Open | 28-Apr-2026 | 1. Login as Admin 2. Ban/freeze a supplier account 3. Login as that supplier | Banned supplier cannot login or use system | Supplier can still login and use system after ban | Critical security flaw
BUG-044 | Security | Supplier can request payout (should be read-only) | SECURITY | HIGH | Supplier Dashboard | Open | 28-Apr-2026 | 1. Login as Supplier 2. Navigate to Finance tab 3. Attempt payout request | Supplier Finance tab is view-only | Supplier can submit payout requests | RBAC violation
BUG-045 | Security | Supplier can publish reviews (should be read-only) | SECURITY | HIGH | Supplier Dashboard | Open | 28-Apr-2026 | 1. Login as Supplier 2. Navigate to Reviews 3. Attempt to publish a review | Reviews are read-only for suppliers | Supplier can publish reviews | RBAC violation
BUG-046 | Supplier Dashboard | Attractions tab missing in Supplier Dashboard | SECURITY | HIGH | Supplier Dashboard | Open | 28-Apr-2026 | 1. Login as Supplier 2. Navigate dashboard menu | Attractions tab visible and accessible | Attractions tab not shown
BUG-047 | Supplier Dashboard | Affiliate Links submission fails with all data entered | PERFORMANCE | HIGH | Supplier Dashboard | In Review | 28-Apr-2026 | 1. Login as Supplier 2. Fill all fields in Affiliate Links form 3. Submit | Form submits successfully | 'Please fill all data' error shown despite all fields completed | False validation error
BUG-048 | Supplier Dashboard | Supplier cannot create activity in Inventory (403 Error) | SECURITY | HIGH | Supplier Dashboard | Open | 28-Apr-2026 | 1. Login as Supplier 2. Go to Inventory 3. Create new activity | Supplier can create activities in their inventory | 403 Forbidden error returned | Permission configuration issue
BUG-049 | Supplier Dashboard | Supplier activities access limited to view-only | SECURITY | HIGH | Supplier Dashboard | In Review | 28-Apr-2026 | 1. Login as Supplier 2. Go to Partner Dashboard activities 3. Try to add/edit/delete | Supplier has full CRUD access to their activities | Only view access available
BUG-050 | Security | Supplier can cancel bookings (should be read-only) | SECURITY | HIGH | Supplier Dashboard | In Review | 28-Apr-2026 | 1. Login as Supplier 2. Navigate to bookings 3. Attempt to cancel | Suppliers have read-only booking access | Supplier can cancel bookings | RBAC violation
BUG-051 | Partner Dashboard | Notifications missing in Partner Dashboard | UI | HIGH | Partner Dashboard | Open | 28-Apr-2026 | 1. Login as Partner 2. Check notifications area | Notifications displayed for bookings, commissions, updates | No notifications shown anywhere in dashboard
BUG-052 | Admin Dashboard | Partner tab does not show all partners | FUNCTIONAL | HIGH | Admin Dashboard | Open | 28-Apr-2026 | 1. Login as Admin 2. Navigate to Partner tab 3. Count listed partners | All registered partners displayed | Only subset appears — some partners missing
BUG-053 | Partner Dashboard | Partner Dashboard not loading | FUNCTIONAL | CRITICAL | Partner Dashboard | Rejected | 28-Apr-2026 | 1. Login as Partner 2. Navigate to Partner Dashboard | Dashboard loads fully with all partner data | System does not respond or fails to load
BUG-054 | Supplier Dashboard | Supplier form accepts invalid input (Company Name/Phone) | UI | HIGH | Supplier Dashboard | Rejected | 27-Apr-2026 | 1. Open supplier registration form 2. Enter numbers in Company Name 3. Enter email in Phone Number field | Validation rejects invalid input types | Company Name accepts numbers; Phone accepts email addresses | Missing field validation
BUG-055 | Supplier Dashboard | Supplier form accepts invalid input (functional) | FUNCTIONAL | HIGH | Supplier Dashboard | Open | 27-Apr-2026 | 1. Open supplier registration form 2. Enter numbers in Company Name 3. Enter email in Phone Number | Form validates input types correctly | Invalid inputs accepted without error
BUG-056 | User Profile | Customer photo feature not working | UI | MEDIUM | Website | Rejected | 27-Apr-2026 | 1. Navigate to profile 2. Click 'Choose Photo' | File picker opens for photo selection | No response — file picker doesn't open
BUG-057 | Security | Mass account creation abuse possible | SECURITY | CRITICAL | Website | In Review | 27-Apr-2026 | 1. Attempt to create large number of accounts rapidly | Rate limiting or CAPTCHA prevents mass account creation | Unlimited accounts created without restriction | Enables fake account attacks
BUG-058 | Auth | Password field accepts spaces | UI | HIGH | Website | Rejected | 27-Apr-2026 | 1. Go to signup 2. Enter password with spaces | Spaces rejected in password field | Spaces accepted as valid input | Missing validation
BUG-059 | Auth | Account created after internet reconnect without confirmation | FUNCTIONAL | CRITICAL | Website | Rejected | 27-Apr-2026 | 1. Start signup 2. Disconnect internet mid-process 3. Reconnect | User must retry/confirm action after reconnecting | Account created automatically without user action | Unexpected behavior
BUG-060 | Auth | Login with Facebook not working | FUNCTIONAL | CRITICAL | Website | Rejected | 27-Apr-2026 | 1. Click 'Login with Facebook' | Facebook OAuth flow initiated successfully | Authentication fails — no access granted
BUG-061 | Auth | Login with Google not working | FUNCTIONAL | CRITICAL | Website | In Review | 27-Apr-2026 | 1. Click 'Login with Google' | Google OAuth flow initiated successfully | Authentication fails — no access granted
BUG-062 | Security | Signup accepts duplicate phone numbers | SECURITY | HIGH | Website | Rejected | 27-Apr-2026 | 1. Register account with phone number 2. Register another account with same number | Error: 'Phone number already registered' | Duplicate phone accepted without error | Missing uniqueness validation
BUG-063 | Security | Checkout page repeats after internet reconnect | SECURITY | CRITICAL | Website | Rejected | 27-Apr-2026 | 1. Start ticket checkout 2. Disconnect internet 3. Reconnect | Checkout resumes once from saved state | Checkout page displayed multiple times | Could cause duplicate charges
BUG-064 | Performance | System freezes on internet disconnect | PERFORMANCE | CRITICAL | Website | In Review | 27-Apr-2026 | 1. Start any action (login/booking) 2. Disconnect internet | Clear error message shown — system remains responsive | System freezes with no error message
BUG-065 | Auth | Duplicate email shows generic error message | UI | HIGH | Website | In Review | 27-Apr-2026 | 1. Signup with already registered email | Error: 'This email is already registered' | Generic error: 'Something went wrong during signup' | Unhelpful UX
BUG-066 | Security | Signup accepts temporary/disposable email addresses | SECURITY | CRITICAL | Website | Resolved | 27-Apr-2026 | 1. Signup using mailinator.com or tempmail.com address | Disposable emails rejected | Temp emails accepted — no verification | Enables fake account creation
BUG-067 | Security | Login fields retain credentials after login | SECURITY | CRITICAL | Website | Resolved | 27-Apr-2026 | 1. Login successfully 2. Navigate back to login page | Login fields cleared after successful login | Email and password still visible in fields | Exposes credentials on shared devices
BUG-068 | Auth | Missing loading indicator during login | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Enter credentials 2. Click Login 3. Observe response | Loading spinner shown during authentication | No indicator. Page appears static until redirect
BUG-069 | Auth | Password conditions don't disappear after valid input | FUNCTIONAL | HIGH | Website | In Review | 27-Apr-2026 | 1. Go to signup 2. Enter a fully valid password meeting all conditions | Password condition hints disappear after conditions met | Conditions remain visible until submit button clicked
BUG-070 | Auth | Username field accepts unlimited characters | UI | HIGH | Website | Open | 27-Apr-2026 | 1. Go to signup 2. Enter very long username (500+ chars) | Character limit enforced (e.g. max 50 chars) | Unlimited input accepted | Missing length validation
BUG-071 | Auth | Phone number field accepts email address during signup | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Go to signup 2. Enter email address in phone number field | Validation rejects non-numeric/invalid phone format | Email accepted as valid phone number
BUG-072 | Auth | Signup allows blank first and last name | UI | HIGH | Website | Resolved | 27-Apr-2026 | 1. Go to signup 2. Leave first/last name empty 3. Submit | Validation error: 'Name is required' | Form submits with empty names
BUG-073 | Security | Email address accepted as password during signup | SECURITY | CRITICAL | Website | Open | 27-Apr-2026 | 1. Go to signup 2. Enter email address as password | Password policy rejects email-formatted passwords | Email accepted as password | Violates basic security standards
BUG-074 | Security | Blocked user still able to book tickets | FUNCTIONAL | CRITICAL | Admin Dashboard | In Review | 27-Apr-2026 | 1. Admin blocks a user account 2. Blocked user logs in 3. Attempts to book ticket | Blocked user cannot login or book | Blocked user successfully books tickets | Block not enforced across systems
BUG-075 | Admin Dashboard | Activity capacity accepts negative numbers | FUNCTIONAL | HIGH | Admin Dashboard | In Review | 27-Apr-2026 | 1. Login as Admin 2. Create/edit activity 3. Enter negative value (e.g. -3) in capacity | Validation rejects negative capacity values | Negative numbers accepted without error
BUG-076 | Admin Dashboard | Activity time displays with +3 hour offset | FUNCTIONAL | HIGH | Admin Dashboard | Open | 27-Apr-2026 | 1. Login as Admin 2. Create activity at 10:00 3. View created activity | Activity displays at 10:00 as entered | Activity shows 13:00 — 3 hour offset | Timezone mismatch between input and display
BUG-077 | Admin Dashboard | Activity price change triggers media validation error | FUNCTIONAL | HIGH | Admin Dashboard | Open | 27-Apr-2026 | 1. Login as Admin 2. Edit an activity 3. Change the price 4. Save | Price updated successfully | Error: 'media: Invalid input' — requires phone field workaround | Unrelated field blocks price edit
BUG-078 | UI | Placeholder text cut off in search bar | UI | LOW | Website | Open | 27-Apr-2026 | 1. View search bar placeholder text under 'WHERE TO?' | 'City, attraction, activity' shown in full | Text truncated to 'City, attraction, acti'
BUG-079 | Cart | Cart retains tickets after logout in another tab | UI | HIGH | Website | Open | 27-Apr-2026 | 1. Open two browser tabs 2. Logout from tab 1 3. Check tab 2 cart | Cart cleared on logout across all tabs | Tab 2 still shows previously added tickets after logout | Session not synchronized across tabs
BUG-080 | Cart | Checkout session lost after language change | UI | HIGH | Website | Open | 27-Apr-2026 | 1. Start checkout process 2. Change website language | Checkout session preserved across language change | Error: 'No Checkout Session' — user must restart booking
BUG-081 | Auth | Name field accepts mixed Arabic and English characters | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Go to signup 2. Enter name with both Arabic and English characters | Validation enforces consistent single language input | Mixed language input accepted
BUG-082 | Auth | Name field accepts numeric input | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Go to signup 2. Enter numbers in first/last name (e.g. '12', '45') | Validation rejects numeric names | Numbers accepted as valid name input
BUG-083 | Auth | Checkout error redirects to browser page instead of site home | SECURITY | MEDIUM | Website | Open | 27-Apr-2026 | 1. Logout 2. Try to access checkout page 3. Click 'Go Back' on error message | User redirected to Tourzina homepage | User redirected to Chrome start page — outside the website | Breaks navigation flow
BUG-084 | Cart | Checkout progress lost after page refresh | UI | HIGH | Website | Open | 27-Apr-2026 | 1. Start checkout — fill contact info 2. Proceed to step 2 (payment) 3. Refresh page | Progress preserved or user prompted to confirm refresh | Returned to step 1 — all data lost
BUG-085 | Security | Cart persists after clearing browser cookies | SECURITY | HIGH | Website | Open | 27-Apr-2026 | 1. Add tickets to cart 2. Clear all browser cookies 3. Revisit site | Cart cleared when cookies are cleared | Cart still shows previous tickets | Session handling flaw
BUG-086 | Cart | Cart emptied after login during checkout | UI | HIGH | Website | Open | 27-Apr-2026 | 1. Logout 2. Add tickets to cart 3. Proceed — prompted to login 4. Login | Cart preserved after login redirect | Cart emptied. User redirected to home page
BUG-087 | Security | Checkout redirects to home page after login | SECURITY | HIGH | Website | Open | 27-Apr-2026 | 1. Logout 2. Try to order tickets 3. Login when prompted | User returned to checkout with cart intact | User sent to homepage. Cart empty
BUG-088 | Cart | Cart deletes previous tickets when adding new destination | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Add ticket for destination A 2. Add ticket for destination B | Both tickets remain in cart | Destination A tickets deleted when B is added | Prevents multi-destination booking
BUG-089 | Booking | Checkout flow resets to ticket selection page on back | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Select tickets and proceed with checkout 2. Navigate back | Previous checkout step shown | Reset to initial ticket time selection page | Loses all progress
BUG-090 | UI | Duplicate calendar widgets displayed on page | UI | MEDIUM | Website | Open | 27-Apr-2026 | 1. Navigate to search/booking page 2. Observe calendar widgets | Single calendar widget displayed | Two calendar widgets shown simultaneously | User confused about which to use
BUG-091 | Wishlist | Wishlist displays same image for all tickets | UI | HIGH | Website | Open | 27-Apr-2026 | 1. Add multiple tickets from different destinations to wishlist 2. View wishlist | Each ticket shows its own relevant image | Same single photo used for all tickets | Misleading visuals
BUG-092 | Cart | Cart not updated after checkout completion | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Add tickets to cart 2. Complete checkout successfully | Cart cleared after successful order | Same items remain in cart post-checkout | Creates user confusion about order status
BUG-093 | Checkout | Card expiry date field accepts invalid input | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Go to checkout payment step 2. Enter '12' in expiry date field | Validation requires full MM/YY format | Only 2 digits accepted — incomplete format allowed | Payment security issue
BUG-094 | Checkout | Checkout form validation issues — Name and Phone fields | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Go to checkout contact info 2. Enter 100+ character name 3. Enter 10-digit phone | Name field has character limit; phone validates format properly | Unlimited name characters accepted; 10-digit phone accepted
BUG-095 | User Profile | Name change feature not working and no input validation | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Go to settings 2. Change account name 3. Save | Name updated and displayed correctly with character limit | Name not updated. Old name persists. Unlimited text accepted in field
BUG-096 | Auth | Date of birth field allows invalid future dates | FUNCTIONAL | MEDIUM | Website | Open | 27-Apr-2026 | 1. Go to registration 2. Select a future date in Date of Birth field | Future dates rejected in Date of Birth | Future dates accepted without error | Invalid data stored
BUG-097 | User Profile | Delete account feature not working | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Login 2. Go to settings 3. Click Delete Account | Account deleted with confirmation message | Feature does not function — account remains active
BUG-098 | User Profile | Change password feature not working | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Login 2. Go to settings 3. Attempt to change password | Password updated successfully | Feature fails to function
BUG-099 | Notifications | Review Reminders notification not working | UI | MEDIUM | Website | Open | 27-Apr-2026 | 1. Go to Notification Preferences 2. Activate Review Reminders | Review reminders triggered and delivered | Feature does not work — no reminders sent
BUG-100 | UI | No feedback after changing currency or language in settings | UI | HIGH | Website | Open | 27-Apr-2026 | 1. Go to settings 2. Change currency or language 3. Observe response | Confirmation message shown after saving preferences | No response or confirmation — unclear if changes applied
BUG-101 | Auth | Password reset link leads to error page | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Click 'Forgot Password' 2. Enter email 3. Open reset link from email | Password reset page loads correctly | Reset page fails to load — error displayed | User completely locked out
BUG-102 | Auth | Logout does not redirect to original page | FUNCTIONAL | MEDIUM | Website | Open | 27-Apr-2026 | 1. Navigate to any page 2. Logout | User returned to page they were on before login | No proper redirection after logout
BUG-103 | Auth | Session active but login prompt shown simultaneously | FUNCTIONAL | HIGH | Website | Open | 27-Apr-2026 | 1. Login 2. Navigate back to previous page | Consistent session state — no re-login prompt if already logged in | Session active but email/password fields prompt re-entry | Confusing inconsistent behavior
BUG-104 | Security | Missing email ownership verification during sign-up | SECURITY | HIGH | Website | Open | 27-Apr-2026 | 1. Signup with any email address 2. Check if verification email sent | Verification email sent to confirm ownership | No verification email sent — any email accepted | Enables registration with others' emails

## By Module
BUGS BY MODULE & SEVERITY
Module | Critical | High | Medium | Low
1 | 7 |  | 1
3 | 11 | 3
2 | 2
| 9 | 2
2
1
1
2 | 4 | 1
1
1
2
2
7 | 10
5
7
| 2 | 1 | 1
| 3 | 1
2 | 2
| 1 | 3
1

## By Platform
BUGS BY PLATFORM & STATUS
Platform | Total | Open | In Review | Resolved | Rejected
Admin Dashboard | 12 | 6 | 4 | 1 | 1
Partner Dashboard | 7 | 3 | 1 | 1 | 2
Staff Dashboard | 5 | 0 | 2 | 0 | 3
Supplier Dashboard | 11 | 6 | 4 | 0 | 1
Website | 69 | 34 | 22 | 5 | 8